## Backlog
|  | Planning | [7 empty] | Tracking
| User Stories | Assignee | Milestone | Story Points | Effort | Resources | Duration | Priority | Dependency | Sprint | Start Date | End Date
1 | As a user, the system should be easy to use so that users can navigate and complete the tasks easily
1.1 | Issue 1.1 - UX UI Design: Dashboard Page | Alvin
1.2 | Issue 1.2 - UX UI Design: Calendar Page
2 | As a user, the system should be secure and tamper proof so that unauthorised users will not be able to impersonate or gain access to the system
2.1 | Issue 2.1 - Login using 2FA | Vinok
3 | As a student, the system should allow me to set alarms to remind them that lesson date in advance so that they will not miss their lessons
3.1 | Issue 3.1 - Code logic for students to set alarm reminder | Zhi Wei
4 | As a student, the system should warn me if my attendance falls below the requirements of a module so that i will be aware about it
4.1 | Issue 4.1 - Code logic for the system to notify students of situations such as attendance falls below module requirements
5 | As a student, the system should be allow me to view a summary of my attendance for all modules in the current trimester so that i'm able to know whether my attendance meets the requirements | Zhi Wei
5.1 | Issue 5.1 - Code logic to store all the summary of all modules in the current trimester for students
5.2 | Issue 5.2 - Display stats in the form of text or graphs for students
6 | As a adminstrator and lecturer, the system should allow me to view the attendance for a lesson and the overall attendance in the current trimester. The stats will be shown as charts | Zhi Wei
6.1 | Issue 6.1 - Code logic to store the attendance for a lesson and overall attendance in the current trimester for admin and lecturer
6.2 | Issue 6.2 - Display stats in the form of text or graphs for admin and lecturer
7 | As a adminstrator, the system should allow me to set up lesson time, location and student list so that students will be able to select the relevant fields when they are submitting their attendance
7.1 | Issue 7.1 - Code logic to input and store all lesson time,location and student list for administrator
7.2 | Issue 7.2 - Code logic to update attendance status accordingly after attendance submission
8 | As a administrator, the system should allow me to set a attendance spot check manually to check the number of students that are physically present in the lesson
8.1 | Issue 8.1 - Code logic to set attendance spot check for admin | Zhi Wei
8.2 | Issue 8.2 - Code logic to update attendance status accordingly after attendance submission for admin
9 | As a administrator, the system should allow me to amend Student's attendance as students who are absent have 48 hrs to submit an excuse request
9.1 | Issue 9.1 - Code logic to allow administrator to amend students attendance 48 hrs after lesson start | Zhi Wei
9.2 | Issue 9.2 - Code logic to update attendance status accordingly after adminstrator have rejected or approved the studen's excuse request
9.3 | Issue 9.3 - Database to retrieve excuse details such as supporting documentation, excuse application status, excuse description
9.4 | Issue 9.4 - Stats should be updated after the admin have amended the attendance
10 | As a student, the system should capture and update my attendance within 1 minute so that my attendance status is accurate
10.1 | Issue 10.1 - Code logic to store the attendance status in a database for students
10.2 | Issue 10.2 - Attendance status is updated in a database within 1 minute after students have subimitted their attendance
10.3 | Issue 10.3 - Database to store attendance details afte students have submitted their attendance
10.4 | Issue 10.4 - Stats should be updated after it has been updated in the database
11 | As a student, the system should allow me to submit my attendance within a 15 min window after lesson start as it will automatically marked students late after that
11.1 | Issue 11.1 - Code logic that marks the student's attendance status as present when the student have submitted within 15 mins after lesson start | Zhi Wei
11.2 | Issue 11.2 - Code logic that marks the student status as Late or absent when the student does not submit their attendance or submit it after the 15 min window
12 | As a student, the system should allow me to apply for excuse 2 days after lesson start so that my attendance status will not be marked as absent
12.1 | Issue 12.1 - Code logic for the student to apply for excuse 2 days after lesson start | Zhi Wei
12.2 | Issue 12.3 - Database to store excuse details such as supporting documentation, excuse application status, excuse description
12.3 | Issue 12.3 - Code logic to update the excuse application status when the administrator have approved or rejected the application
13 | As a adminstrator, the system should allow me to amend their attendance status up to 7 days after the lesson as students may have a valid reason for missing lesson | Zhi Wei
13.1 | Issue 13.1 - Code logic for the administrator to amend a student's attendance status 7 days after lesson start
13.2 | Issue 13.2 - Code logic for the student's attendance status to be updated if there is any amendment by the administrator
13.3 | Issue 13.3 - Stats should be updated if there is any amendment by the administrator
14 | As a lecturer, the system should allow me to amend Student's attendance up till midnight on lesson day as their attendance status may change during the lesson | Zhi Wei
14.1 | Issue 14.1 - Code logic for the administrator to amend a student's attendance status till midnight after lesson start
14.2 | Issue 14.2 - Code logic for the student's attendance status to be updated if there is any amendment by the lecturer
14.3 | Issue 14.3 - Stats should be updated if there is any amendment by the lecturer